## Slide 1: Risk Management Training

## Slide 2: Risk Management Process
Reporting
Planning
Risk management
Supporting process
Internal process
ADDED VALUE
Strengthen planning
Facilitate reporting
Enable monitoring

## Slide 3: EUI Risk Management Framework
Based on ISO 31000:2018
PDCA approach
RMF - single document:
  Risk Management Policy
  Risk Management Process
  3 Annexes
* President Decision No. 12/21 regarding the administrative organisation of the EUI
Responsibility
President
CRO – SG*
Risk owner/ contact points (optional)
All members and non-members
Management Team
Tools
Central Risk Register
  At corporate level
  At unit level
Submission template
Cloud-based solution
Use Excel

## Slide 4: EUI Risk Management Framework
Timing
Corporate: once per year with annual planning
Unit: continuous, CRR update once per month
Evaluation of Risk Management Process
Corporate: once per year with annual reporting
Unit: once per year with annual reporting
Role of CRO
Additional exercise
Superpower

## Slide 5: Central Risk Register (CRR)

## Slide 6
Risk ownership/ID risk
Risk: The effect of uncertainty on the achievement of objectives*
Risk owner: Head of Unit responsible for the risk.
  Abbreviations 18+1
  Unique number
  Identification year
Choose your unit
Every risk must have an owner
Unique identification of every risk example: IAO/1/2019
* Risk management - Guidelines ISO 31000:2018

## Slide 7: Central Risk Register (CRR)

## Slide 8
Unit’s objectives
Risk: The effect of uncertainty on the achievement of objectives.

## Slide 9: Central Risk Register (CRR)

## Slide 10: Risk definition
RISK = EVENT + THREAT + IMPACT

## Slide 11: Risk definition
“Failure to take-off correctly (EVENT)
because of adverse weather conditions (THREAT)
resulting in potential death (IMPACT)”.
RISK = EVENT + THREAT + IMPACT
Risk: Plane crash

## Slide 12: Risk definition
Example 1: Risk: Lack of human resources
No human resources
Frequent changes in faculty members and gaps in teaching continuity EVENT
Frequent changes in faculty members and gaps in teaching continuity due to long recruitment processes THREAT
Frequent changes in faculty members and gaps in teaching continuity due to long recruitment processes causing limited variety and quality of the doctoral programme IMPACT.
RISK = EVENT + THREAT + IMPACT

## Slide 13: Risk definition
Forward looking exercise risk ≠ issue
Linked to objectives
EVENT – THREAT – IMPACT event ≠ threat
Useful phrases:
  … due to … … caused by… because of… (THREAT)
  … following … causing … resulting in … (IMPACT)
Starting point: your activities - EVENT
Use of bold font for description of EVENT
Be precise
Useful hints

## Slide 14: Central Risk Register (CRR)

## Slide 15
Untreated
Assess Impact (I) and Likelihood (L) 1 to 5
Risk assessment calculated automatically (I x L)
Risk analysis - Inherent risk
Don’t touch grey columns
Without controls

## Slide 16
Risk analysis – Inherent risk
Risk rating
Likelihood
1-5
Impact
1-5

## Slide 17: Central Risk Register (CRR)

## Slide 18
Control: measure that maintains and/or modifies risk*
  include, but are not limited to, any process, policy, device, practice, or other conditions and/or actions which maintain and/or modify risk
Typical examples:
  Financial controls, segregation of duties, delegation of authorities
  Guidelines, procedures, manuals, standard forms
  4 EYE principle
  Window, door, lock,
  Academic Programme,
  Approval (signature), authorisation
Risk analysis - Existing controls
Existing controls
Use “Alt” + “Enter”
* Risk management - Guidelines ISO 31000:2018

## Slide 19: Central Risk Register (CRR)

## Slide 20
Risk analysis - Residual risk
Assess impact and likelihood 1 to 5 – apply criteria
Risk assessment calculated automatically
Don’t touch grey columns
Residual risk assessment column – reference point
With controls

## Slide 21: Risk analysis
Inherent risk > Residual risk
  Ideal
Inherent risk = Residual risk
  Check (quality of) controls
Inherent risk < Residual risk
  ?
  Stop damaging (reputation of the) EUI
Useful hints

## Slide 22: Central Risk Register (CRR)

## Slide 23
Act:
  Mitigate
  Avoid
  Share Planned actions
  Transfer
  Exploit/Enhance
Accept Justify and Monitor
Risk evaluation/treatment
Accept or Act?

## Slide 24
Analysis of trend – risk vs cost
Risk evaluation/treatment
Common traps – high cost
Chart: Time
| T0 | T1 | T2
Control | 1 | 5 | 10
Risk | 10 | 5 | 1

## Slide 25
Analysis of trend – risks over time
Risk evaluation/treatment
Common traps – unrealistic picture
Chart: Time
| T0 | T1 | T2 | T3 | T4
In reality | 9 | 8 | 8 | 10 | 9 | 7 | 6 | 5 | 7
Optimistic scenario | 9 | 8.5 | 8 | 7 | 6 | 5 | 4 | 3 | 2

## Slide 26
Zero risk not possible
When “Act”, weigh future benefits against costs
Costs > future benefits, choose “Accept” the risk
Not all Planned Actions have to be successful
When “Act”, Be SMART
Whatever you chose, justify your decision
Risk evaluation/treatment
Useful hints

## Slide 27
SMART
  Specific ≠ “strengthen our efforts”
  Measurable ≠ “excellent, exceptional”
  Assignable ≠ “EUI will”
  Relevant ≠ “N/A”
  Time-bound ≠ “in future”
Risk evaluation/treatment
Useful hints

## Slide 28: Risk Management
Good practices:
Keep it simple
Be able to justify your assessments
Internal process – not external
You are risk owner / an expert but not your risks – Share them (register)
Input from everybody

## Slide 29: Thank you